## Slide 1
Board Meeting
December 19, 2024

## Slide 2: Three-Part Wildfire Damage Mitigation Project
Bipartisan Infrastructure Law, the U.S. Department of Energy’s
GRID RESILIENCE AND INNOVATION PARTNERSHIPS PROGRAM
(GRIP) Grant
Award Notice October 17, 2023
Award Accepted September 15, 2024
Project Management Plan Approved December 17, 2024
Project Completion Deadline September 30, 2029

## Slide 3: Project Team Members
Mora-San Miguel Electric Cooperative
Transmission & Distribution Services, LLC
New Mexico Rural Electric Cooperatives
Bolinger, Segers, Gilbert & Moss
Thomson Consulting Services

## Slide 4: PROJECT FOCUS
Modernize and Strengthen MSMEC’s grid by accelerating and expanding current work*
Power line system maintenance and upgrades (grid hardening)
Implement new technology (grid modernization)
Tree clearing in high priority areas beyond ROW (enhanced vegetation management)
*does not include any work covered by FEMA

## Slide 5: Primary Goals and Expected Results
Decrease the number and duration of power outages
Harden and modernize the grid to withstand and recover faster from wildfires and other climatic events
Equip the grid to be able to adapt to increases in demand and local renewable energy
Increase the value of MSMEC member owned facilities
Increase the number of quality jobs at MSMEC and in the community

## Slide 6: Project Benefits
INVESTMENTS in the system that will not affect the operating budget
NEW EMPLOYEES for the Project includes adding a complete maintenance crew and support staff
EMPLOYEE TRAINING on operation and ongoing maintenance for mapping, work management, accounting, distribution automation and more
DOCUMENTED PLANS for construction standards, vegetation management and grid hardening/moderdization
ACCELERATE WORK to meet project deadlines using contractors help where and when needed

## Slide 7: Project Phases
Project timeline is December 2024-December 2029
Phase 1 Design Permitting and Siting
  Distribution system unmanned system assessment
  Field system inventory
  Distribution modeling and mapping
  Vegetation management plan
  Coordination study and implementation plan
Phase 2 Procurement and Acquisition of Materials and Services
Bidding, purchasing and acquisition
  System software
  Certified arborist
  Tree clearing work
  Landowner support
  Distribution materials
  Hiring employees
Phase 3: Construction and Deployment
Tree marking and vegetation management implementation
Distribution hardening/modernization implementation
Phase 4: Testing and Commissioning
Train employees in all areas to maintain vegetation management and grid hardening/modernization plans
Continuation of vegetation and grid hardening/modernization implementation

## Slide 8: Team Members and Roles
Planned Activities by SOPO Task/Subtask Number(s) | 
Organization Name Mora-San Miguel Electric Cooperative, Inc. (MSMEC) | 
1.0 - Project Management, Planning, and Community Benefits: Project Management Plan (1.1); Community Benefits Plan (1.2); NEPA Compliance (1.3) Regulatory Approvals (1.4) 2.0 – System Assessment: Assist and collaborate with T&D field personnel with the assessment of the electric distribution vegetation conditions (2.1) and collaborate and/or assist T&D with the Field System Inventory (2.2). 3.0 – Mapping & Coordination Study: Collaborate with T&D field personnel on the development of System Model (3.1) and the subsequent Coordination Study (3.2). 4.0 – Enhanced Vegetation Management: Collaborate with certified arborist and project team staff to identify the best approach for vegetation management (4.1). 5.0 – Grid Modernization/Hardening: Collaborate with T&D on the: Distribution Line Hardening Design (5.1); Distribution Automation Implementation determination (5.2); Work Management Information System (5.3); Identify a Preferred Vendors List for Grid Hardening/Modernization (5.4); Distribution System Hardening/Modernization Plan (5.5). 6.0 – Mapping and Coordination Study: System Software Purchase (6.1). 7.0 – Application of Enhanced Vegetation Management: Collaborate with and/or assist T&D in the process to Bid for Certified Arborist (7.1); Enhanced Vegetation Management Work Bidding (7.2); Landowner Support (7.3). | 8.0 – Grid Modernization/Hardening: Order Distribution Materials (8.1); Hire new employees and order ancillary materials. (8.2). 9.0 – Application of Enhanced Vegetation Management Plan: Collaborate with the project team on the Enhanced Vegetation Project Coordination and Management (9.1); Field Coordination; (9.2). 10.0 – Grid Modernization/Hardening: Coordinate with project team (10.1); Completion of construction field work (10.2); Work Management Implementation. (10.4); Distribution Automation Implementation. (10.5); Distribution Line Hardening Implementation. (10.6). 11.0 – Training: Participate in Mapping and Coordination Training (11.1); Participate in Distribution Automation Training (11.2); Participate in Work Management Information System Training (11.3) 12.0 - Continuation of Enhanced Vegetation Management Plan: Continuing Work Plan (12.1) 13.0 - Continuation of Grid Modernization/Hardening Plan: Ensure continuation of the Grid Hardening/Modernization plan and scheduled patrol, pole inspection, and maintenance. Subtask 13.1- Construction Standards: Use and continually update as needed.

## Slide 9: Team Members and Roles (continued)
Organization Name New Mexico Rural Electric Cooperatives (NMREC) | 
1.0- Project Management, Planning, and Community Benefits: Will assist the recipient in managing and directing the project in accordance with the accepted PMP (1.1); Will assist the recipient with the coordination of activities to effectively implement the CBP goals (1.2) | 
Organization Name Thompson Consulting Services | 
1.0- Project Management, Planning, and Community Benefits: Will compile and submit reporting required by DOE to include Davis Bacon and Related Acts. | 
Organization Name Transmission & Distribution Services, LLC (T&D) | 
2.0 – System Assessment: Unmanned Aerial System Assessment (2.1) perform an assessment of the electric distribution vegetation conditions utilizing LiDAR and aerial imagery; Field System Inventory (2.2). 3.0 – Mapping & Coordination Study: System Model (3.1), Coordination Study (3.2). 4.0 – Enhanced Vegetation Management: Enhanced Vegetation Management Plan (4.1). 5.0 – Grid Modernization/Hardening: Distribution Line Hardening Design (5.1); Distribution Automation Implementation determination (5.2); Work Management Information System (5.3); Identify a Preferred Vendors List for Grid Hardening/Modernization (5.4); Distribution System Hardening/Modernization Plan (5.5). 7.0 – Application of Enhanced Vegetation Management: Bid for Certified Arborist (7.1); Enhanced Vegetation Management Work Bidding (7.2); Landowner Support (7.3). | 8.0 – Grid Modernization/Hardening: Order Distribution Materials determined by coordination study (8.1); Hire new employees and order ancillary materials (8.2). 9.0 – Application of Enhanced Vegetation Management Plan: Enhanced Vegetation Project Coordination and Management (9.1); Field Coordination (9.2). 10.0 – Grid Modernization/Hardening: Project Coordination and Management. (10.1); Completion of construction field work (10.2); Work Management Implementation. (10.4); Distribution Automation Implementation. (10.5); Distribution Line Hardening Implementation. (10.6). 11.0 – Training: Mapping and Coordination Training (11.1); Distribution Automation Training (11.2); Subtask 11.3: Work Management Information System Training (11.3).
Organization Name Bolinger Segars Gilbert and Moss | 
Subtask 11.4 - Accounting Support and Training: Provide training and accounting support to ensure accounting compliance onsite and virtual (11.4) | 

## Slide 10: Project Schedule
SOPO Task/ Subtask Number | SOPO Task/ Subtask Title | Planned Start Date | Planned Completion Date | Team Member
1.0 | Project Management, Planning, and Community Benefits | 9/1/2024 | 12/31/2029 | MSMEC//T&D/NMREC/Thompson
1.1 | Project Management Plan (PMP) | 9/1/2024 | 10/31/2024 | Complete
1.2 | Community Benefits Plan | 9/1/2024 | 10/31/2024 | Complete
1.3 | National Environmental Policy Act (NEPA) Compliance | 9/1/2024 | 8/31/2026 | T&D
2.0 | System Assessment | 1/1/2025 | 6/30/2025 | 
2.1 | Unmanned Aerial System Assessment | 1/1/2025 | 4/30/2025 | T&D
2.2 | Field System Inventory | 3/1/2025 | 6/30/2025 | MSMEC/T&D
3.0 | Mapping and Coordination Study | 7/1/2025 | 12/31/2025 | 
3.1 | System Model | 7/1/2025 | 10/31/2025 | T&D
3.2 | Coordination Study | 11/1/2025 | 12/31/2025 | T&D
4.0 | Enhanced Vegetation Management | 1/1/2026 | 3/31/2026 | 
4.1 | Enhanced Vegetation Management Plan | 1/1/2026 | 3/31/2026 | MSMEC/T&D
5.0 | Grid Modernization/Hardening | 1/1/2026 | 4/30/2027 | 
5.1 | Distribution Line Hardening Design | 1/1/2026 | 4/30/2026 | T&D
5.2 | Distribution Automation Implementation Determination | 5/1/2026 | 4/30/2027 | MSMEC/T&D

## Slide 11: Project Schedule
5.3 | Work Management Information System | 8/1/2026 | 10/31/2026 | T&D
5.4 | Identify a Preferred Vendors List for Grid Hardening/Modernization | 11/1/2026 | 12/31/2026 | MSMEC/T&D
5.5 | Distribution System Hardening/Modernization Plan | 1/1/2027 | 3/31/2027 | MSMEC/T&D
6.0 | Mapping and Coordination Study | 4/1/2027 | 9/30/2027 | 
6.1 | System Software Purchase | 4/1/2027 | 9/30/2027 | T&D
7.0 | Application of Enhanced Vegetation Management | 4/1/2026 | 4/30/2028 | 
7.1 | Bid for Certified Arborist | 4/1/2026 | 7/31/2026 | T&D
7.2 | Enhanced Vegetation Management Work Bidding | 6/1/2026 | 4/30/2028 | T&D
7.3 | Landowner Support | 4/1/2026 | 4/30/2028 | MSMEC/T&D
8.0 | Grid Modernization/Hardening | 7/1/2027 | 10/31/2028 | 
8.1 | Order Distribution Materials | 7/1/2027 | 6/30/2028 | MSMEC
8.2 | Hire New Employees and Order Ancillary Materials | 11/1/2025 | 10/31/2028 | MSMEC
9.0 | Application of Enhanced Vegetation Management Plan | 9/1/2027 | 9/30/2029 | 
9.1 | Enhanced Vegetation Project Coordination and Management | 9/1/2027 | 7/31/2029 | MSMEC/T&D
9.2 | Tree Marking and Field Coordination | 9/1/2027 | 7/31/2029 | T&D Subcontractor
9.3 | Perform Vegetation Clearing | 11/1/2027 | 9/30/2029 | T&D Subcontractor

## Slide 12: Project Schedule
10.0 | Grid Modernization/Hardening | 10/1/2027 | 12/31/2029 | 
10.1 | Project Coordination and Management | 10/1/2027 | 2/28/2029 | MSMEC/T&D
10.2 | Coordination Study Recommendations Implementation | 10/1/2027 | 7/31/2028 | MSMEC/T&D
10.4 | Work Management Implementation | 12/1/2028 | 2/28/2029 | MSMEC/T&D
10.5 | Distribution Automation Implementation | 3/1/2029 | 12/31/2029 | MSMEC/T&D
10.6 | Distribution Line Hardening Implementation | 2/1/2028 | 12/31/2029 | MSMEC/T&D
11.0 | Training | 2/1/2029 | 7/31/2029 | 
11.1 | Mapping and Coordination Training | 6/1/2029 | 7/31/2029 | T&D
11.2 | Distribution Automation Training | 6/1/2029 | 7/31/2029 | T&D
11.3 | Work Management Information System Training | 6/1/2029 | 7/31/2029 | T&D
11.4 | Accounting Support and Training | 2/1/2029 | 7/31/2029 | T&D
12.0 | Continuation of Enhanced Vegetation Management Plan | 2/1/2029 | 7/31/2029 | MSMEC
12.1 | Continuing Work Plan | 2/1/2029 | 7/31/2029 | MSMEC
13.0 | Continuation of Grid Modernization/Hardening Plan | 2/1/2029 | 7/31/2029 | MSMEC
13.1 | Construction Standards | 5/1/2029 | 7/31/2029 | T&D

## Slide 13
Questions? Concerns? Suggestions? Comments?
All input collected will be documented and shared during monthly team project meetings to see how it could be incorporated into the project
Ongoing opportunities for providing input and getting project information and updates
Annual Meetings
Monthly Board Meetings
Project webpage in https://morasanmiguel.coop (coming soon)
Contact Jason Trujillo, Jtrujillo@morasanmiguel.coop