## Slide 1: Award Kickoff Meeting
DE-FOA-2740
November 18, 2024

## Slide 2: Introduction
Project Title: Three-Part Wildfire Damage Mitigation Project
Prime Recipient: Mora-San Miguel Electric Cooperative (MSMEC or Recipient)
DE-FOA-2740: DE-GD0000893
Federal Project Officer: Brayden S. Rumsey
Business Point of Contact: Les Montoya
Principal Investigator: Jason Trujillo

## Slide 3: Project Overview
The focus of the Wildfire Damage Mitigation Project is to modernize and strengthen MSMEC’s grid by accelerating and expanding grid hardening, grid modernization and vegetation management. The results of this project will enable MSMEC to better prevent, withstand and recover from power disruptions, especially those caused by wildfires. This will ultimately benefit members in a service territory comprised of nearly 100% disadvantaged communities (DAC’s).
Primary Goals and Expected Results
Decrease the number and duration of electric disruptions
Harden and modernize the grid to withstand and recover faster from wildfires and other climatic events
Equip the grid to be able to adapt to increases in demand and interconnecting with local renewable energy
Increase the value of MSMEC member owned facilities
Increase the number of quality jobs at MSMEC and in the community

## Slide 4: Project Phases
Throughout the project MSMEC, with its partners, will perform project management, planning and community benefits. MSMEC is responsible for obtaining NEPA and other regulatory approvals, as necessary. Project timeline is December 2024-December 2029.
Phase 1 Design Permitting and Siting
  Distribution system unmanned system assessment
  Field system inventory
  Distribution modeling and mapping
  Vegetation management plan
  Coordination study and implementation plan
Phase 2 Procurement and Acquisition of Materials and Services
Bidding, purchasing and acquisition
  System software
  Certified arborist
  Tree clearing work
  Landowner support
  Distribution materials
  Hiring employees
Phase 3: Construction and Deployment
Tree marking and vegetation management implementation
Distribution hardening/modernization implementation
Phase 4: Testing and Commissioning
Train employees in all areas to maintain vegetation management and grid hardening/modernization plans
Continuation of vegetation and grid hardening/modernization implementation

## Slide 5: Cost Summary
Budget Category | Federal Share | Non-Federal Share | Total
Personnel | $248,687 | $4,074,947 | $4,323,634
Fringe Benefits | $2,548,763 | - | $2,548,763
Travel | - | - | -
Equipment | $3,386,086 | - | $3,386,086
Supplies | $20,000 | - | $20,000
Contractual | $5,024,682 | - | $5,024,682
Remaining Contractual | $32,000 | - | $32,000
Construction | - | - | -
Other | $9,975 | - | $9,975
Sub-Total Direct Charges | $11,270,193 | - | $15,345,140
Indirect Charges | - | - | -
Total | $11,270,193 | $4,074,947 | $15,345,140

## Slide 6: Cost Breakdown – Contractual Valued at $25,000 or more (All Federal Share)
Single Audits - $37,500
Accounting Support - $93,000
Grant Administration / Compliance / Communication Support - $237,600
Unmanned Aerial System Vegetation Assessment - $90,000
Field System Inventory Overhead - $520,000
Field System Inventory Underground - $299,500
ESRI / WindMil System Model - $250,000
Coordination Study - $250,000
Vegetation Management Plan - $50,000
Distribution Line Hardening Pole Testing - $288,000
Distribution Line Hardening Design - $85,000
Distribution Line Hardening Standards Book for Avian Protection & Construction - $100,000
Distribution Automation Implementation Determination Study - $30,000
Work Management Information System Implementation - $30,000
Vegetation Management Work - $50,000
Landowner Support - $70,000
Substation RTU Installation - $27,000
Vegetation Project Coordination - $60,000
Vegetation Clearing - $252,286
Coordination Study Implementation Design - $135,000
Distribution Hardening Pole Change Out - $440,700
Coordination Study Implementation - $1,429,096
Distribution Automation Engineering Services - $50,000
Work Management Implementation - $60,000
Mapping and Coordination Training - $45,000
Work Management Information System Training - $45,000

## Slide 7: Team Members and Roles
Planned Activities by SOPO Task/Subtask Number(s) | 
Organization Name Mora-San Miguel Electric Cooperative, Inc. (MSMEC) | 
1.0 - Project Management, Planning, and Community Benefits: Project Management Plan (1.1); Community Benefits Plan (1.2); NEPA Compliance (1.3) Regulatory Approvals (1.4) 2.0 – System Assessment: Assist and collaborate with T&D field personnel with the assessment of the electric distribution vegetation conditions (2.1) and collaborate and/or assist T&D with the Field System Inventory (2.2). 3.0 – Mapping & Coordination Study: Collaborate with T&D field personnel on the development of System Model (3.1) and the subsequent Coordination Study (3.2). 4.0 – Enhanced Vegetation Management: Collaborate with certified arborist and project team staff to identify the best approach for vegetation management (4.1). 5.0 – Grid Modernization/Hardening: Collaborate with T&D on the: Distribution Line Hardening Design (5.1); Distribution Automation Implementation determination (5.2); Work Management Information System (5.3); Identify a Preferred Vendors List for Grid Hardening/Modernization (5.4); Distribution System Hardening/Modernization Plan (5.5). 6.0 – Mapping and Coordination Study: System Software Purchase (6.1). 7.0 – Application of Enhanced Vegetation Management: Collaborate with and/or assist T&D in the process to Bid for Certified Arborist (7.1); Enhanced Vegetation Management Work Bidding (7.2); Landowner Support (7.3). | 8.0 – Grid Modernization/Hardening: Order Distribution Materials (8.1); Hire new employees and order ancillary materials. (8.2). 9.0 – Application of Enhanced Vegetation Management Plan: Collaborate with the project team on the Enhanced Vegetation Project Coordination and Management (9.1); Field Coordination; (9.2). 10.0 – Grid Modernization/Hardening: Coordinate with project team (10.1); Completion of construction field work (10.2); Work Management Implementation. (10.4); Distribution Automation Implementation. (10.5); Distribution Line Hardening Implementation. (10.6). 11.0 – Training: Participate in Mapping and Coordination Training (11.1); Participate in Distribution Automation Training (11.2); Participate in Work Management Information System Training (11.3) 12.0 - Continuation of Enhanced Vegetation Management Plan: Continuing Work Plan (12.1) 13.0 - Continuation of Grid Modernization/Hardening Plan: Ensure continuation of the Grid Hardening/Modernization plan and scheduled patrol, pole inspection, and maintenance; Construction Standards: Use and continually update as needed (13.1).

## Slide 8: Team Members and Roles
Organization Name New Mexico Rural Electric Cooperatives (NMREC) | 
1.0- Project Management, Planning, and Community Benefits: Will assist the recipient in managing and directing the project in accordance with the accepted PMP (1.1); Will assist the recipient with the coordination of activities to effectively implement the CBP goals (1.2) | 
Organization Name Transmission & Distribution Services, LLC (T&D) | 
2.0 – System Assessment: Unmanned Aerial System Assessment (2.1) perform an assessment of the electric distribution vegetation conditions utilizing aerial imagery; Field System Inventory (2.2). 3.0 – Mapping & Coordination Study: System Model (3.1), Coordination Study (3.2). 4.0 – Enhanced Vegetation Management: Enhanced Vegetation Management Plan (4.1). 5.0 – Grid Modernization/Hardening: Distribution Line Hardening Design (5.1); Distribution Automation Implementation determination (5.2); Work Management Information System (5.3); Identify a Preferred Vendors List for Grid Hardening/Modernization (5.4); Distribution System Hardening/Modernization Plan (5.5). 7.0 – Application of Enhanced Vegetation Management: Bid for Certified Arborist (7.1); Enhanced Vegetation Management Work Bidding (7.2); Landowner Support (7.3). | 8.0 – Grid Modernization/Hardening: Order Distribution Materials determined by coordination study (8.1); Hire new employees and order ancillary materials (8.2). 9.0 – Application of Enhanced Vegetation Management Plan: Enhanced Vegetation Project Coordination and Management (9.1); Field Coordination (9.2). 10.0 – Grid Modernization/Hardening: Project Coordination and Management. (10.1); Completion of construction field work (10.2); Work Management Implementation. (10.4); Distribution Automation Implementation. (10.5); Distribution Line Hardening Implementation. (10.6). 11.0 – Training: Mapping and Coordination Training (11.1); Distribution Automation Training (11.2); Subtask 11.3: Work Management Information System Training (11.3).
Organization Name Bolinger Segars Gilbert and Moss | 
Subtask 11.4 - Accounting Support and Training: Provide training and accounting support to ensure accounting compliance onsite and virtual (11.4) | 

## Slide 9: Project Schedule
SOPO Task/ Subtask Number | SOPO Task/Subtask Title | Planned Start Date | Planned Completion Date | Planned Total Cost (DOE and Cost Share)
1.0 | Project Management, Planning, and Community Benefits | 9/1/2024 | 12/31/2029 | $1,570,983
1.1 | Project Management Plan (PMP) | 9/1/2024 | 10/31/2024 | -
1.2 | Community Benefits Plan | 9/1/2024 | 10/31/2024 | -
1.3 | National Environmental Policy Act (NEPA) Compliance | 9/1/2024 | 8/31/2026 | -
2.0 | System Assessment | 1/1/2025 | 6/30/2025 | $1,756,687
2.1 | Unmanned Aerial System Assessment | 1/1/2025 | 4/30/2025 | -
2.2 | Field System Inventory | 3/1/2025 | 6/30/2025 | -
3.0 | Mapping and Coordination Study | 7/1/2025 | 12/31/2025 | $676,354
3.1 | System Model | 7/1/2025 | 10/31/2025 | -
3.2 | Coordination Study | 11/1/2025 | 12/31/2025 | -
4.0 | Enhanced Vegetation Management | 1/1/2026 | 3/31/2026 | $194,654
4.1 | Enhanced Vegetation Management Plan | 1/1/2026 | 3/31/2026 | -

## Slide 10: Project Schedule
SOPO Task/ Subtask Number | SOPO Task/Subtask Title | Planned Start Date | Planned Completion Date | Planned Total Cost (DOE and Cost Share)
5.0 | Grid Modernization/Hardening | 1/1/2026 | 4/30/2027 | $719,329
5.1 | Distribution Line Hardening Design | 1/1/2026 | 4/30/2026 | -
5.2 | Distribution Automation Implementation Determination | 5/1/2026 | 4/30/2027 | -
5.3 | Work Management Information System | 8/1/2026 | 10/31/2026 | -
5.4 | Identify a Preferred Vendors List for Grid Hardening/Modernization | 11/1/2026 | 12/31/2026 | -
5.5 | Distribution System Hardening/Modernization Plan | 1/1/2027 | 3/31/2027 | -
6.0 | Mapping and Coordination Study | 4/1/2027 | 9/30/2027 | $329,009
6.1 | System Software Purchase | 4/1/2027 | 9/30/2027 | -
7.0 | Application of Enhanced Vegetation Management | 4/1/2026 | 4/30/2028 | $225,422
7.1 | Bid for Certified Arborist | 4/1/2026 | 7/31/2026 | -
7.2 | Enhanced Vegetation Management Work Bidding | 6/1/2026 | 4/30/2028 | -
7.3 | Landowner Support | 4/1/2026 | 4/30/2028 | -

## Slide 11: Project Schedule
SOPO Task/ Subtask Number | SOPO Task/Subtask Title | Planned Start Date | Planned Completion Date | Planned Total Cost (DOE and Cost Share)
8.0 | Grid Modernization/Hardening | 7/1/2027 | 10/31/2028 | $3,343,623
8.1 | Order Distribution Materials | 7/1/2027 | 6/30/2028 | -
8.2 | Hire New Employees and Order Ancillary Materials | 11/1/2027 | 10/31/2028 | -
9.0 | Application of Enhanced Vegetation Management Plan | 9/1/2027 | 9/30/2029 | $1,089,790
9.1 | Enhanced Vegetation Project Coordination and Management | 9/1/2027 | 7/31/2029 | -
9.2 | Tree Marking and Field Coordination | 9/1/2027 | 7/31/2029 | -
9.3 | Perform Vegetation Clearing | 11/1/2027 | 9/30/2029 | -
10.0* | Grid Modernization/Hardening | 10/1/2027 | 12/31/2029 | $2,932,755
10.1 | Project Coordination and Management | 10/1/2027 | 2/28/2029 | -
10.2 | Coordination Study Recommendations Implementation | 10/1/2027 | 7/31/2028 | -
10.4 | Work Management Implementation | 12/1/2028 | 2/28/2029 | -
10.5 | Distribution Automation Implementation | 3/1/2029 | 12/31/2029 | -

## Slide 12: Project Schedule
SOPO Task/ Subtask Number | SOPO Task/Subtask Title | Planned Start Date | Planned Completion Date | Planned Total Cost (DOE and Cost Share)
10.6 | Distribution Line Hardening Implementation | 2/1/2028 | 12/31/2029 | -
11.0 | Training | 2/1/2029 | 7/31/2029 | $951,525
11.2 | Distribution Automation Training | 6/1/2029 | 7/31/2029 | -
11.3 | Work Management Information System Training | 6/1/2029 | 7/31/2029 | -
11.4 | Accounting Support and Training | 2/1/2029 | 7/31/2029 | -
12.0 | Continuation of Enhanced Vegetation Management Plan | 2/1/2029 | 7/31/2029 | $777,504
12.1 | Continuing Work Plan | 2/1/2029 | 7/31/2029 | -
13.0 | Continuation of Grid Modernization/Hardening Plan | 2/1/2029 | 7/31/2029 | $777,504
13.1 | Construction Standards | 5/1/2029 | 7/31/2029 | -
*In numbering the subtasks for 10, the number of 10.3 inadvertently skipped.

## Slide 13: Project Metrics
SOPO Task/ Subtask Number | Tracking Metric | Units (%, $, #, etc.) | Goal for Phase
3.0 | Number of feeders participating in coordination study | # | ≥ 5
5.0 | Improve System Average Interruption Duration Index (SAIDI) | Minutes/year | Reduce by >5%
5.0 | Improve System Average Interruption Duration Index (SAIFI) | Interruptions/year | Reduce by >5%
9.3 | Vegetation clearing completion rate | % | >75%
10.5 | Number of distribution automation devices installed | # | ≥100
11.0 | Percentage of relevant staff trained on new systems | % | 100%
12.1 | Reduction in vegetation-related outages | % | Improve by >5%

## Slide 14: Milestones
Milestone Number | Milestone (or Decision Point) | SOPO Task/ Subtask Number | Planned Completion Date | Verification Method (or Decision Criteria)
M1 | Project Management Plan and Community Benefits Plan approved | 1.1, 1.2 | 01/31/2025 | DOE approval of submitted plans
M2 | NEPA compliance documentation accepted | 1.3 | 04/30/2026 | Receipt of NEPA clearance from DOE
M3 | System assessment completed with 95% coverage | 2.1, 2.2 | 05/31/2025 | Assessment report submitted and approved by project team
DP1 | Go/No-Go: Proceed with detailed planning based on system assessment | 2.0, 3.0 | 08/15/2025 | Decision Criteria: Assessment coverage ≥95%, data quality meets project standards
M4 | System model and coordination study completed | 3.1, 3.2 | 01/31/2026 | Final model and study report approved by utility engineering team
M5 | Enhanced Vegetation Management Plan finalized | 4.1 | 04/30/2026 | Plan document approved by utility management and relevant stakeholders
M6 | Grid Modernization/Hardening Design completed | 5.1, 5.2, 5.3, 5.5 | 04/30/2027 | Design documents and implementation plan approved by utility engineering team
DP2 | Go/No-Go: Proceed with major procurement and implementation | 5.0, 6.0, 7.0, 8.0 | 05/15/2027 | Decision Criteria: Design meets technical requirements, budget estimates within 10% of original projections
M7 | 50% of planned vegetation management work completed | 9.1, 9.2, 9.3 | 06/30/2028 | Progress report verified by project management team
M8 | 50% of distribution automation devices installed and operational | 10.5 | 12/31/2028 | Installation report and system testing results
M9 | 10,000 poles tested for grid hardened | 10.6 | 06/30/2029 | Pole testing completion report and field verification
DP3 | Go/No-Go: Evaluate project impact and decide on potential scope expansion | 10.0, 12.0, 13.0 | 07/15/2029 | Decision Criteria: SAIDI and SAIFI improvements ≥5%, positive community feedback
M10 | All planned staff training programs completed | 11.1, 11.2, 11.3, 11.4 | 12/31/2029 | Training completion certificates for all relevant staff
M11 | Construction standards manual published and implemented | 13.1 | 09/30/2029 | Manual publication and distribution to relevant departments
M12 | Project completion with final report submitted | All | 12/31/2029 | DOE acceptance of final project report

## Slide 15: Project Deliverables
SOPO Task / Subtask Number | Deliverable | Planned Completion Date
1.1 | Project Management Plan | 10/31/2024
1.2 | Community Benefits Plan | 10/31/2024
1.3 | NEPA Compliance (if applicable) | 8/31/2026
1.4 | Regulatory Approvals | As required
2.0 | System Assessment | 6/30/2025
3.1 | Mapping and System Model Report | 10/31/2025
3.2 | Coordination Study | 12/31/2025
4.1 | Enhanced Vegetation Management Plan | 3/31/2026
5.1 | Distribution Line Hardening Plan/Design | 4/30/2026
5.2 | Distribution Automation Plan/Design | 4/30/2027
5.5 | Grid Modernization/Hardening Plan | 3/31/2027
 | Pre-Continuation and Final Briefing Documents | 8/15/2025, 5/15/2027,7/15/2029, 12/31/2029

## Slide 16: Project Risk Assessment
Risk | Likelihood (High, Medium, Low) Impact (High, Medium, Low) | Potential Impact (Identify SOPO Task/Subtask if applicable) | Mitigation Strategy
Delays in obtaining NEPA compliance | Medium High | Task 1.3 - Could delay project start and subsequent tasks | Start NEPA process early, engage experienced consultants, maintain open communication with regulatory agencies
Insufficient aerial assessment coverage due to weather or technical issues | Medium Medium | Task 2.1 - Incomplete system assessment data | Schedule multiple assessment windows, have backup equipment ready, consider alternative assessment methods
Supply chain disruptions affecting procurement of grid modernization materials | High High | Tasks 8.1, 10.0 - Could delay implementation of grid hardening | Identify multiple suppliers, consider stockpiling critical components, develop contingency plans for alternative materials
Shortage of qualified workforce for implementation | Medium High | Tasks 8.2, 10.0 - Could slow down project execution | Develop partnerships with local educational institutions, offer competitive compensation, implement robust training programs
Unexpected technical challenges in integrating new grid modernization technologies | Medium High | Task 10.5 - Could delay automation implementation and affect overall project timeline | Conduct thorough testing before full deployment, engage vendors for technical support, maintain flexibility in implementation schedule
Natural disasters or extreme weather events during project execution | Low High | All tasks - Could cause significant delays and damage | Ensure adequate insurance coverage and build in schedule buffers
Budget overruns due to unforeseen circumstances | Medium High | All tasks - Could limit scope of project implementation | Implement cost tracking, maintain contingency fund, prioritize critical components
Community opposition to project activities | Low Medium | Tasks 7.0, 9.0 - Could delay vegetation management and grid modernization efforts | Develop robust community engagement plan, clearly communicate project benefits, address concerns proactively
Regulatory changes affecting project scope or implementation | Low High | All tasks - Could require significant project adjustments | Monitor regulatory environment closely, maintain flexibility in project plans, engage with regulatory bodies proactively